## Slide 1
6th STEERING COMMITTEE
Amman 29 March 2017
ADAPTATION
Project funded by the European Union
4/05/2015

## Slide 2: ADAPTATION OBJECTIVES
Strengthening institutional adaptation capacity
  Adaptation data management and analysis
  Vulnerability assessment
  Adaptation plan development

## Slide 3: From 5th to 6th SC / ADAPTATION
ITEM | ACTION | RESULT
Regional Activity on Climate downscaling/impacts | Jordan, Egypt and Libya are given the possibility of joining the activity, first by benefiting from the remote support /mentoring provided by ClimaSouth, next by participating in the 2nd workshop proposed for Nov 2015 (Consortium) | 2nd downscaling impact seminar taken place in Lecce 02 – 06 November 2015. Handbooks prepared and circulated on the platform
Regional Seminar on Vulnerability (assessment methods and tools) | Thematic topic for seminar (Nov 2015) may be defined, possibly groundwater (Consortium) | Tools and methods for Vulnerability Assessment regional seminar held in Milan 02 – 05 February 2016. Follow up exercise ongoing
Regional Seminar on Adaptation, 2016 (need for climate change impact assessment, strengthening resilience to climate hazards, adaptation measures at the national level) | To be formatted. To include exchange of experiences / good practices on adaptation among local players working at the local level (Consortium) | To be decided

## Slide 4: From 4th to 5th SC / ADAPTATION
ITEM | ACTION | RESULT
Tunisia / national activity | The 3 concepts identified following the national workshop to be ranked by order of priority (Tunisia). Then, taking the ranking into account, and through further communication with Tunisia, it is anticipated that one concept will be developed into the Tunisian National Activity (Consortium) | Pending. Could also be considered to steer it towards coastal vulnerability assessment and adaptation planning? Link to vulnerability tools regional seminar
Egypt / national activity | Focus for ClimaSouth on the design of the CC centre of excellence; the SLR component now primarily to be implemented through UNDP (some collaboration with ClimaSouth still anticipated, given the SLR component expected to be part of the CC centre of excellence). ToRs to be finalized and activity launched (Consortium) | Ongoing: Selection of Experts. Activities expected to end in autumn 2016

## Slide 5: From 4th to 5th SC / ADAPTATION
ITEM | ACTIVITY | RESULT
Algeria / National Activity | Agreement on proposed activity (downscaling of CC scenarios for forestry sector, especially fire risk) ToRs to be finalized and activity launched (Consortium) | Activity launched and in full swing. Expected to end late autumn 2016. Good example of activity that could have a regional/sub-regional dimension. Adaptation/mitigation (and livelihood) co-benefits
Lebanon / National Activity (not included) | Strengthen the institutional capacity of LARI through enhancement of EWS | Concept note implemented and National Activity redrafted. Implementation expected until summer 2016
Palestine / National Activity (not included) | Vulnerability assessment coastal zone and/or economic impacts of climate change | Deliver a base of further adaptation planning. To start right after the Steering Committee!