## Slide 1
6th STEERING COMMITTEE
Amman 29th March 2017
GENERAL
Project funded by the European Union
4/05/2015

## Slide 2: CLIMASOUTH ESSENTIALS
Project extended until 31 January 2018, with funds increase of 700.000 Euro (almost official…)
Scale up and/or replication and/or completion of ongoing national and regional activities in:
Support access to climate finance
Support for NDC implementation (including MRV)
Support for climate adaptation to enhance resilience

## Slide 3: From 5th to 6th SC (and beyond) / GENERAL
ITEM | ACTION (lead entity) | RESULT | TO JANUARY 2018
Sharing of ROM report | Share ROM report | ROM report shared | 
Coordination with other EU initiatives | Enhance coordination | Joint side events COP22; News sharing; UfM meetings; field visit… | Continue coordination; joint initiatives
Implementation of the Paris Agreement | Explore practical implications of the Paris Agreement for CS countries Explore national/regional approaches Maximize effectiveness for results | MRV regional survey and pilot implementation at national level (Lebanon) (I)NDC regional survey Focus on actions for concrete results (climate finance; project proposal follow up; intensification of activities implementation; …) | Regionalization of lessons learnt and best practices How best proceed on further NDC implementation support?
Next steering committee | Early 2017 | Implemented 29 March 2017 | Final regional meeting to capitalize on results