## Slide 1
6th STEERING COMMITTEE
Amman March 29 March 2017
Mitigation and Climate Finance
Project funded by the European Union
4/05/2015

## Slide 2: From 5th to 6th SC (and beyond) / Mitigation and Climate Finance
ITEM | ACTION | RESULT | TO JANUARY 2018
Jordan National Activity | Continue development of Solar Water Pump project proposal | Second draft ready. Strong adaptation component included | Pilot implementation with EUD funds. Link to financiers
Egypt National Activity | Implement feasibility study for Climate Change Centre of Excellence | Study almost completed. COP22 side event | Workshop with international donors
Israel National Activity | Second round of LEAP | LEAP scheduled and suspended (more funds needed) | Rescheduling of LEAP
NAMA/MRV regional seminar | Fact finding/gap analysis and regional seminar | MRV survey implemented (policy paper on the website). Pilot action for MRV intranet under implementation in Lebanon | Lessons learnt/best practices form pilot action for presentation at final regional seminar
CC Mainstreaming/NDC implementation | Public and private sector engaged in solutions for climate change | Support for the implementation of the Lebanon Climate Act/LCA | Continue support LCA and regionalize the results (handbook under preparation)

## Slide 3: From 5th to 6th SC (and beyond) / Mitigation and Climate Finance
ITEM | ACTIVTY | RESULT | TO JANUARY 2018
Regional seminar for climate finance | Hold Regional Seminar | Regional seminar implemented, project selection in interested countries, “Access to climate finance” Handbook prepared, support for project development under implementation in 4 countries (Algeria, Jordan, Lebanon, Palestine) | Continue support to selected projects for development and matching with funds. Support to new projects?
Climate finance mechanisms | Enhance availability of and access to climate funding | Two policy papers (available on website) on international and national climate finance in Israel | Support for Action Plan on key findings. Regionalization of promising opportunities
Climate finance mechanisms | Regionalization of promising opportunities | Explore feasibility of establishing a Mediterranean Mitigation Bond | Establishment of mitigation bond and presentation at COP23